## Sheet 1
Test Plan Table
Test Number | Test Description | Planned to check | Test Result (Pass/Fail) | Notes
1 | Test LE timers and interrupts | 04-15-2025 | Pass(100%) | LE timer and I2C interrupt are happening at a regular delay as defined in the FSM
2 | Read data and conversion of sensor data | 04-18-2025 | Pass(100%) | Able to read data from Luminosity, pressure, temperature, and humidity, conversion needs to be taken care of during BLE implementation
3 | Verify the FSM transition and deterministic state for each sesnor | 04-19-2025 | Pass(100%) | Able to successfully do a transition
4 | Bluetooth Connection establishment and close functionality | 04-23-2025 | Pass(100%) | Low powe node able to connect and publish data to the GATT services, verified using SI connect app
5 | SD card logging with timestamp | 04-24-2025 | Failed(100%) | Able to write to the SD card, timestamp, and standalone worked, but code integration failed
6 | Sensor services enable and disable of indication and read data once connected | 04-25-2025 | Pass(100%) | Receiving all sensor data successfully
7 | LCD test | 04-26-2025 | Pass(100%) | Able to test the BLE address, connection status, and sensor status
8 | Low power mode current measurement | 04-27-2025 | Pass(100%) | Measured using the SI energy profiler
9 | Final full system testing | 04-28-2025 | Pass(100%) | Everything worked as expected apart from SD card logging
Overall : 100%